## R1→R2 Branch Strategy
R1 → R2 Branch Strategy — Environment Sync
Environment sync across Sprint 4, Sprint 5, Sprint 6 (R1) → Sprint 1, Sprint 2, Sprint 3 (R2)
Release | Environment | Sprint | Branch / Stage | Deployment | Copy Type | Sync / Promotion Action | Target Branch | Status | Notes
R1 | DEV | Sprint 4 | R1 DEV | Continuous Deploy | Partial Copy | — | — | Active | Developer triggers deploy; partial copy to DEV org
|  | Sprint 5 | R1 DEV | Continuous Deploy | Partial Copy | — | — | Active | Continues from Sprint 4 via Continuous Deploy
|  | Sprint 6 | R1 DEV | Continuous Deploy | Partial Copy | — | — | Active | Sprint 6 DEV; feeds Branch Promotion to UAT Branch
| QA | Sprint 4 | R1 QA | Continuous Deploy | Partial Copy | — | — | Active | Promoted from R1 DEV at Sprint 4 end
|  | Sprint 5 | R1 QA | Continuous Deploy | Partial Copy | R1 QA → R2 QA (sync) | R2 QA | Active | Promoted from R1 DEV Sprint 5; synced to R2 QA
|  | Sprint 6 | R1 QA | Continuous Deploy | Partial Copy | — | — | Active | R1 QA Sprint 6 continuous deploy; feeds R1 UAT Sprint 6
| UAT | Sprint 4 | — (not active) | — | — | — | — | Not Active | UAT not yet started in Sprint 4
|  | Sprint 5 | UAT Branch | Branch Promotion | Partial Copy | R1 QA → UAT Branch | UAT Branch | Active | UAT Branch created via Branch Promotion at end of Sprint 5; intermediate staging
|  | Sprint 6 | R1 UAT Sprint 6 | Org Creation | Full Copy | UAT Branch → R1 UAT | R1 UAT | Active | Branch Promotion from UAT Branch → R1 UAT Sprint 6; Full Copy SIT/UAT deploy. Continues Deploy active
R2 | DEV | Sprint 4 (R1) | Not Started | — | — | — | — | Not Started | R2 track not yet initiated
|  | Sprint 5 (R1) | R2 DEV Till Sprint 4 | Continuous Deploy | Partial Copy | R1 QA → R2 DEV (Branch Promotion) | R2 DEV | Active | R2 DEV initialized via Branch Promotion from R1 QA end of Sprint 5
|  | Sprint 6 (R1) | R2 DEV Sprint 5 → Sprint 6 | Continuous Deploy | Partial Copy | — | — | Active | R2 DEV Sprint 6 continues from Sprint 5 state
|  | Sprint 1 (R2) | R2 DEV Sprint 6 | Continuous Deploy | Partial Copy | — | — | Active | R2 sprint cadence begins; labeled Sprint 1 on R2 timeline
|  | Sprint 2 (R2) | R2.2.2 DEV | Continuous Deploy | Partial Copy | — | — | Active | Sub-sprint R2.2.2 DEV deploy
|  | Sprint 3 (R2) | R2.3 DEV | Continuous Deploy | Partial Copy | — | — | Active | R2.3 DEV stage; feeds R2 UAT at end
| QA | Sprint 4 (R1) | Not Started | — | — | — | — | Not Started | R2 QA not yet active
|  | Sprint 5 (R1) | R2 QA Sprint 5 | Branch Promotion | Partial Copy | R2 DEV → R2 QA (Branch Promotion) | R2 QA | Active | Branch Promotion from R2 DEV; also receives R1 QA → R2 QA sync
|  | Sprint 6 (R1) | R2 QA Sprint 6 | Continuous Deploy | Partial Copy | — | — | Active | R2 QA Sprint 6 continuous deploy
|  | Sprint 1 (R2) | R2 QA Sprint 6 | Continuous Deploy | Partial Copy | — | — | Active | R2 QA continues into R2 Sprint 1
|  | Sprint 2 (R2) | R2.2 QA | Continuous Deploy | Partial Copy | — | — | Active | R2.2 QA sub-sprint
|  | Sprint 3 (R2) | R2.3 QA | — | Partial Copy | R2.3 QA → R2 UAT (Branch Promotion) | R2 UAT | Active | Final QA stage; Branch Promotion triggers R2 UAT
| UAT | Sprint 3 (R2) | R2 UAT (R1 will now R2 UAT) | Continuous Deploy | Full Copy | R2.3 QA → R2 UAT ¦ R1 UAT → R2 UAT | R2 UAT | Active | End-state UAT for full R2 release; R1 UAT also transitions to R2 UAT. Full Copy deploy. Continues →

## Key Changes vs v1
What changed in this diagram vs previous?
1. UAT Branch node added
Sprint 5 now shows a UAT Branch intermediate stage created via Branch Promotion from R1 QA
Previously the first diagram went straight from R1 QA Sprint 6 to R1 UAT Sprint 6
2. R1 QA Sprint 5 syncs to R2 QA (not R2 DEV)
The sync arrow label in this diagram reads R1 QA → R2 QA (visible in Sprint 5 area)
Previous diagram showed R1 QA → R2 DEV as the sync target
3. R2 UAT end-state: R1 will now become R2 UAT
The diagram labels this node 'R1 will now R2 UAT' indicating R1 UAT merges into R2 UAT
Both R2.3 QA → R2 UAT (Branch Promotion) and R1 UAT → R2 UAT are captured in the table

## Legend
Legend — Color Coding
Label | Fill | Meaning
R1 DEV |  | R1 Development environment rows
R1 QA |  | R1 QA environment rows
R1 UAT |  | R1 UAT environment rows (incl. UAT Branch)
R2 DEV |  | R2 Development environment rows
R2 QA |  | R2 QA environment rows
R2 UAT |  | R2 UAT environment rows
Active |  | Deployment is active and running
Not Active |  | Environment lane not yet started or skipped
Not Started |  | Release track not yet initiated